## Sheet1
Marsha Thole 856-3352 | PLANNING CALENDAR FOR TRIBUTE 25
2009-05-03 |  |  |  |  | Updated:
WHAT | WHEN | DATE | DAY | TIME | LOCATION
2009
Meeting | April | 14 | TUE | 1600 | Airman & Fam Readiness Ctr KAFB
Registration List Clean-up | May /June | ?? |  |  | Mary, Ethel, Marsha
Meeting | May | 12 | 1600 | 1600 | Safety Center
Meeting | June | 9 | TUE | 1600 | Safety Center
No meeting | July | TBA | ? | ? | Small group meets to work on registration packet (with 2 other events)
No meeting | August
Meeting | September | 8 | TUE | 1600
Meeting | October | 20 | TUE | 1600
Meeting | November | 10 | TUE | 1600 | Stuff envelopes
MAIL OUT ENVELOPES | November | 30 | MON |  | Done by VA
Meeting | December | 8 | TUE | 1500 | Christmas Party
2010
EARLYBIRD DEADLINE | January | 13 | FRI
Meeting | January | 12 | TUE | 1600
Meeting | January | 26 | TUE | 1600
Tea | January | TBD | TBD | 1100
Meeting | February | 9 | TUE | 1100 | Meet at MVC for lunch and review layout/plans
Talk on Cathay Williams | February | 12 | FRI |  | MVC for breakfast
REGULAR DEADLINE | February | 17 | FRI
Meeting | February | 23 | TUE | 1500 | Stuff tote bags
Meeting | March | 2 | TUE | 1600
Set-up at MVC | March | 4 | THU | 1430 | MVC
Dinner with Keynote | March | 4 | THU | 1730 | MVC
MAIN EVENT | March | 5 | FRI | 0600 | MVC
Meeting | March | 16 | TUE | 1600 | Post-Tribute 25 Wrap-up