## Sheet1
| TRIBUTE XXVI – 2011 |  |  |  | as of 2/5/2011
Countdown Schedule – 25th Anniversary
| Black = Information or confirmed Red = Action Needed/Pending (Based on "Done" column) |  |  |  | WEBSITE:
www.TributeToWomenintheMilitary.org
# | COMMITTEE | DATE | EVENT | POC | COMMENTS, REMARKS, NOTES
1 | CHAIR | April | Confirm date of Tribute for next year | ALL | Friday, 4 Mar 2011 | 2010-09-14
2 | FACILITY | April | Confirmed date with Mountain View club | Marlene Mathis |  | 2010-09-14
3 | ALL | April | Appoint a Chair | ALL | Elaine Gonzales | 2010-09-14
4 | CHAIR | April | Distribute new Countdown Sched before mtg | Chair
5 | ALL | April | Appoint a Vice Chair
6 | VICE CHAIR | April | Update Committee Membership Roster & Org Chart | Vice Chair
7 | CHAIR | April | Review the VOLUNTEER JOB DESCRIPTION and attendance policy. Members to perform several tasks, check this schedule regularly, keep the appropriate people informed | Chair | Volunteers need to RSVP for each meeting to the Chair/Vice Chair
8 | CHAIR | April | Go over the new Vertical Org Listing | Chair
9 | ALL | April | Discuss possible workshop speakers and initiate speaker search | ALL | APD Self Defense - Ethel Tilley - Daedalion Room Health Fair - Gloria Sampson Held in Hardin Room | 2010-09-14
10 | REGISTRATION | April | Assign coordinator for: Registration | Ethel Tilley | Subcommittee needs 5 people day of event | 2010-09-14
11 | SCHOLARSHIP | April | Establish Scholarship Committee | Chair | Subcommittee needs 5 people for reviewing nominations, including 2 AD | 2010-09-14
12 | CHAIR | April | Assign coordinator for: PR - on base (includes tenant units, Guard/Reserve) | Ethel Tilley Gloria Chavez-Sampson |  | 2010-09-14
13 | CHAIR | April | Assign coordinator for: PR - off base | Christin Barden |  | 2010-09-14
14 | CHAIR | April | Assign a VARO Coordinator | Diana Wong | Need liaison with the VARO—coordinate w/Linda Shank on VARO mailing costs, envelopes (need by Nov mtg, take stuffed env. To VARO)
15 | CHAIR | April | Assign coordinator for: Graphics | Kelly Aldrich | Graphics: Kelly Aldrich | 2010-09-14
16 | CHAIR | April | Assign coordinator for: FINANCE | Mary Cox | Finance: Mary Cox | 2010-09-14
17 | CHAIR | April | Assign master coordinator for: Doorprizes/ Silent Auction items, Tote bag donations | Diana Wong Christin Barden | Possible Purse Auction | 2010-09-14 | Need Volunteer on day of event
18 | CHAIR | April | Assign coordinator for: Facility (MVC) & Food | Marlene Mathis |  | 2010-09-14 | Will bring a menu at Nov meeting
19 | CHAIR | April | Assign assistant on base PR coordinator
20 | CHAIR | April | Assign coordinator for: Signs |  | Signs used on the day of the event. Get list from _________. Review it.
21 | CHAIR | April | Assign coordinator for: Protocol - keynote | Christin Barden | Will coordinate keynote speaker logistics |  | Shoshanna Johnson is our guest speaker (Confirmed)
22 | CHAIR | April | Assign coordinator for: Protocol - on base people | Gloria Chavez-Sampson | Will handle the DV/senior staff
23 | CHAIR | April | Assign coordinator for: Protocol - off base DVs | Ethel Tilley
24 | ARRANGEMENTS | April | Assign coordinator for Inventory | Mary Cox
25 | ARRANGEMENTS | April | Assign coordinator for Morning Refreshments | Marlene Mathis & Diana Wong
26 | CHAIR | April | Assign coordinator for: Volunteers | Ethel Tilley | Need 6 volunteers on day of the event. |  | 2 greeters, 2 silent/purse auction table/1 floater/1 extra. The volunteers meals will be paid for if they are there for the entire event.
27 | Chair | April | Review Org Chart and fill in names for gaps; look at list of tasks to be assigned. | Elaine Gonzales | Not necessary for committee. Useful for day of event.
28 | GRAPHICS | April | Post updated logo to committee web page | Kelly Aldrich |  | 2010-09-14
29 | ALL | April | Select dates for Earlybird registration and regular registration | Kelly (for regis info) | Regular registration deadline - February 17 (postmarked) - After that date, the registration envelope will be returned to the person with a form letter to take their chances on the day of the event. This will be emphasized in the registration packet. | 2010-09-14
30 | ALL | April | Possibilities for keynote speaker; confirm by May or June | Christin Barden | Possible Guest Speakers: *Former Marine - Dr. Betty Moseley-Brown, Dir Women's Veterans Center, Wash DC. *Former Army - 1st POW ShoShawna Johnson, *Former Army - Tammy Duckworth - double amputee, running for Congress, Chicago * Army Reserve SSgt Genevieve Chase, Founder of American Women Veterans * | 2010-09-14 | Confirmed: Shoshanna Johnson will be our speaker
31 | WEBMASTER | April | Update website with any new info. | Kelly Aldrich |  | 2010-09-14
32 | ALL | April | Discuss possible themes & program format | ALL | Theme: Women In Action | 2010-09-14 | confirmed
33 | DOORPRIZES | May | Establish limit on doorprizes. | Chair | Decided to minimize the # of doorprizes to 5 | 2010-11-04
34 | WEBMASTER | May | Update website with any new info. | Kelly Aldrich |  | 2010-05-01
35 | CHAIR | May | Identify the Top 3 liaison | Chair | MSgt Melissa Edwards (she is also pres) |  | Need to invite to our meetings.
37 | PROGRAM | May | Appoint Emcee | Chair | Laurel Hull (former Marine) confirmed. | 2010-11-05
38 | PROGRAM | May | Morning entertainment | Chair | Diana Wong | 2010-11-05
39 | CHAIR/ V-C | May | Distribute updated Countdown Schedule | Elaine Gonzales |  | 2010-09-14
40 | SIGNS | May | Assign coordinator for: Signs/Posters/Flyers. Get spreadsheet from Elaine | Elaine Gonzales | Need to do our own printing…. | 2010-11-05
41 | CHAIR | June | Assign coordinator for: TWIM Pins | Mary Cox | will order pins in December | 2010-09-14
42 | CHAIR | June | Assign coordinator for: Donut Dudes (1) | Mary Cox |  | 2010-09-14
43 | ARRANGEMENTS | June | Assign coordinator for: Decorations & Centerpieces | Diana Wong | Idea already in mind for centerpiece - Last year's mug with cactus plant w/US or NM flag. Good way to get rid of old coffee mugs. | 2010-11-05
44 | CHAIR | June | Do we need a Staff Summary Sheet? If, so, identify the active duty person who will be the base liaison (to base cmdr’s office) and who will prepare the Staff Summary Sheet. | Elaine Gonzales | Send eSSS to Robert Liddy since we have our guest speaker confirmed. | 2010-11-06
45 | TOTE BAG COORDINATOR | June | Determine colors/style for bags. Order in October) . Model #3242. From 4imprint.com. Tel: 877-446-7744 | Mary | Working on color - possible camouflage | 2010-09-14
46 | CHAIR | June | USO Room | Diana Wong | Doing USO display. Will have placed behind the Donut Dudes. | 2010-09-14
47 | FACILITY | June | Submit renewal of organization status to 377 SVS. Person to see: Moreno Jeannette M Civ 377 SVS/CCA Tel: 846-4128 | Marlene Mathis | The office to coordinate with is: Services Squadron, Bldg – need cy of minutes - need copy of countdown schedule and committee members | 2010-09-14
48 | ALL | September | Identify date in Sept for State Fair Veterans Day. Determine whether TWIM will have a table, and schedule accordingly. | Mary Cox & Diana Wong, Elaine | We will have TTWIM table and flyers about our event. Date set for Thurs, Sep 23. | 2010-09-14
49 | CHAIR | September | Email updated Countdown Schedule | Elaine Gonzales | Reviewed at Sep meeting. | 2010-09-10
50 | SIGNS | September | Review signs list; submit update by email for Sept. |  | Determine how many and where the signs will be posted. Commissary, BX, 377 MSS, 377 SGS, VA Women's Clinic, VARO,
51 | CHAIR | September | Assign coordinator for: Sponsors/Cash Donors | Mary Cox | Working on list
52 | ARRANGEMENTS | September | Assign coordinator for: Ribbons. We get them from: The Ribbon Place, 141C Wyoming NE (Central & Wyoming). Tel: 823-1411. (Check with Mary Cox as to status of what needs to be ordered.) | Mary Cox | We'll use what we have on hand. | 2010-11-04
53 | SCHOLARSHIP | September | Notice: Review Scholarship criteria and propose any changes | Elaine Gonzales | Need to establish scholarship committee
54 | GRAPHICS/ Vice Chair | September | Draft the registration forms packet; confirm final in Nov. Email form to everyone. | Elaine & Kelly Aldrich | Will review at Nov meeting | 2010-11-04
55 | ALL | September | Complete tentative program with opening Morning Ceremonies | Kelly Aldrich |  | 2010-11-01
56 | CHAIR | September | Morning Ceremonies - Color Guard - Who? | Diana Wong
57 | Vice Chair | September | Email updated Countdown Schedule and seek additional committee members (if necessary). | Chair or Vice Chair
58 | Scholarship | September | Draft of info to go into Scholarship Package to be sent out in Oct | Elaine Gonzales |  | 2010-12-01
59 | OPERATIONS | September | Email VARO to check whether they will provide envelopes for Tribute mailing in Dec. | Mary Cox
60 | PR | October | Master PR Plan for remainder of 2009 & 2010 due. Need where press release will go, including other bases, local and other town newspapers. Include: retirement homes, senior citizen centers, Indian Pueblos, schools with JROTC & ROTC, Jubilee & Alegria active adult communities, the ABQ J SAGE.
61 | ALL & FACILITY/ FOOD | October | Select the 3 meal options. | Marlene Mathis | Marlene is checking with Club to see if we can have 3 options.
62 | PROGRAM | October | Finalize morning entertainment | Elaine GOnzales | Call Rebecca Linda Smith for the National Anthem. (Done, confirmed) | 2010-11-10
63 | PROGRAM | October | Assign the Chaplain Coordinator: (1) | Ethel Tilley | emailed chaplain | 2010-11-04
64 | TOTE BAGS | October | Start contacting places for tote bag goodies commitment. | ALL
65 | PR - ON BASE | October | Final on-base PR plan due
66 | PR- OFF BASE | October | Final off-base PR plan due
67 | TREASURER | October | Establish budget based on projected income (sponsors and fees) and estimated expenses | Mary Cox
68 | LIAISON | October | If not already identified, who is the Top 3 liaison person? | TOP 3
69 | SCHOLARSHIP | October | Chair & Regis review previous year's ltr on awards instructions & program to cmdrs/div chiefs. Make any corrections. Last wk in Nov - Distribute call for nominations for awards and advertise awards and criteria | Elaine & Ethel
70 | SIGNS | November | Get work orders to Printing for posters/flyers/signs. | Mary Cox
71 | CHAIR | November | Write sponsor request letter to Sandia National Lab (Lockheed). Check with Pam Katanach. Also, request to Kirtland Fed Credit Union, Sandia Area Fed C.U., and Sandia Laboratory Fed C.U., and NM Educators Fed C.U. | Mary Cox
72 | CHAIR | November | Write big article for Nucleus, to be published in the first week of December. Include info on the awards program and our website. | Laurel/Elaine
73 | CHAIR | November | Send info on event to ABQ MOAA, Women Officers. | Marlene Mathis
74 | SIGNS | November | Have final draft of posters and flyer. Make sure copy corresponds with agreed-on deadline date(s) for registration | Elaine & Kelly
75 | FLYERS | November | AGREE ON FLYERS & POSTERS: FLYERS (11x14): BX, VA Regional Ofc – 2 (downtown) lobby; VA Hospital lobby, 377 Med Grp & AF Hospital portion, Sandia Labs, AFOTEC, 58 SOW, Top 3, ANG (2), Navy/Marine/Mary Cox, AFRL, 377 ABW HQ, & MPF/Ethel, Thrift Shop, Mini BX on west side, Mini Mall, BX Beauty Salon, BX Art Gallery, BX Barber Shop, Gym, Clothing Sales, Outdoor Rec FACILITY, Auto Hobby Shop, Fitness Center, KFCU, Sandia Area FCU, Lodging, Youth Center, NCOA, Reserve Center (on Wyoming) – 2, (see main list in Word document), McDonald’s, CAP Office (west side of base), Atomic Museum, Dining FACILITY (mess hall), dormitories, NM Dept of Veterans Services, Women Veterans of NM (Christin McKinley - via email, too), NM Veterans Memorial, American Legion Post 99. Kirtland FCU - on base and the Montgomery location
76 | WEBMASTER | November | Post Registration form on Tribute to TWIM website | Kelly Aldrich |  | 2010-12-01
77 | TABLE CENTERPIECE | November | Identify options for head table centerpieces. | Shirley McGuire
78 | ALL | November | Need volunteer(s) to plan food for Christmas party and pick up | All
79 | PR | November | Draft of final PPT slides for Wg presentation (Needs to be in Dec) | Kelly Aldrich
80 | PROGRAM | November | Morning Ceremonies - Flags | Mary Cox
81 | PROGRAM | November | Morning Ceremonies - vocalist for National Anthem | Elaine | Rebecca Linda Smith will sing National Anthem | 2010-12-01
82 | PROTOCOL | November | Status of eSSS | Elaine | In Wg Exec office | 2011-02-10
83 | Seminar Speaker COORDINATOR | November | Re-confirm seminar speaker availability; send confirmation letter to them | Christin Barden
84 | CHAIR & REGISTRATION | November | Check mailing lists and purge/edit. Begin preparing mailing labels | Ethel Tilley
85 | FINANCE | November | Ltr from Chair for potential donations. Gather complimentary/ advertisement items for registration tote bags | ALL | Ask Kelly if letter needs to be updated.
86 | CHAIR | November | Decide on final registration form | Elaine & Kelly |  | 2010-12-10
88 | ARRANGEMENTS | December | Presentation on the Tribute to the First Term Airman Orientation | Paula Hainesworth
89 | PINS | December | Order pins and other required items | Mary Cox
92 | PROTOCOL | December | Draft invitation letter for DVs
93 | EXHIBITS | December | First notice to potential exhibitors | Kelly Aldrich |  | 2010-01-11
94 | TOTE BAGS | December | Order tote bags. Allow minimum of 3 wks for ordering & receiving. Get new logo from Kelly Aldrich. | Mary
95 | TABLES | December | Identify anything special for the tables | Diana Wong
96 | PR | December | Notify lst Congressional District office to put Tribute on schedule. Info about TWIM to them for their website | Elaine
98 | PR | December | Info about TWIM to NM Dept of Veterans Services for their website
99 | PR | December | Website info for 377ABW (get input from Marsha)
100 | PROTOCOL | December | Update DV list - confirm contact info | Teresa
101 | CHAIR | December | Order plaques for corporate sponsors at Plaque Shop on base | Elaine
102 | WEBMASTER | December | Update website | Kelly Aldrich |  | 2010-12-15
103 | CHAIR/VICE | December | Update Countdown list and distribute | Vice Chair
104 | REGIS & Chair | December | Confirm master registration spreadsheet | Mary/Elaine /Ethel
105 | PROGRAM | December | Color Guard confirmed? | Diana Wong
106 | CHAIR | December | Review Top 3 involvement and TWIM needs | Chair
107 | PR | December | Get Tribute information posted to Sen. Bingaman's website
108 | PR | December | Get Tribute information posted to Sen. Udall's website
109 | PR | December | Get Tribute information posted to ABQ Mayor's website
110 | CHAIR | December | Get Tribute information posted to State Dept of Veterans Affairs website
111 | WEBMASTER | December | Registration materials to final printing | Elaine & Kelly |  | 2010-12-13
112 | CHAIR | December | Establish meeting schedule (date/place) for Jan & Feb 2009. | Chair | Feb 8, 15, 22, 29 @ 4:00 | 2011-02-08
113 | PR | December | Launch advertising campaign, for the base PAO to publicize beginning in Jan. |  | Working with 377 ABW Public Affairs on article | 2011-02-08
114 | PR | December | Review planned publicity for January
115 | SIGNS | December | Status on POSTERS, SIGNS & FLYERS work order | Christina
116 | ALL – BAG STUFFING | December | This is the meeting where we have our holiday party and stuff envelopes. Need to order food for party. White elephant gift exchange: Cannot buy anything, including the wrapping. Bring an item you don't want that is in good condition or never used. | ALL
117 | FACILITY | December | Possibilities for vocalist to sing National Anthem | Elaine | Rebecca Linda Smith will sing National Anthem | 2010-10-12
118 | VICE CHAIR | December | Morning Ceremonies - notify 1st District U.S. House Rep liaison. | Elaine | Spoke to Marsha Garcia | 2011-02-01
119 | SEMINAR COORDINATORS | Jan 1st wk | Identify audio-visual requirements for all participants (keynote speaker, any seminar speakers, etc.) and give to Marlene
120 | CHAIR | Jan 1st wk | Review program schedule thus far. | Chair
121 | TREASURER | Jan 1st wk | Establish who will get the mailbox key to pick up registrations
122 | CHAIR | Jan 1st wk | Plan and schedule ceremony participants - Service Flags | Mary/Diana
123 | FINANCE | Jan lst wk | Tote bags received? | Mary
124 | PR | Jan 1st wk | Status of eSSS
125 | PR | Jan 1st wk | Status of poster/flyer distribution
126 | PROTOCOL | Jan 1st wk | Update on keynote speaker ARRANGEMENTS & get their meal choice if staying for lunch | Teresa
127 | REGISTRATION | Jan 1st wk | Style of name tags | Ethel Tilley
128 | CHAIR | Jan 1st wk | Plan and schedule ceremony participants - Luncheon Chaplain
129 | PROTOCOL | Jan 1st wk | Schedule a 2nd briefing, if necessary, to wing staff
130 | PROTOCOL | Jan lst wk | Invitation to DVs to go out electronically where possible, and in the regular mail for the offbase people | Teresa
131 | VICE CHAIR | Jan 1st wk | Update Countdown list, Org Chart, Membership Roster, and distribute | Vice Chair
132 | EVALUATION | Jan 1st wk | Assign coordinator for evaluations (Diana Wong). Review TWIM evaluations from previous yr-email out old one, along with summary of comments; get comments from Committee, and email proposed changes to everyone in prep for mtg in 2nd wk. | Diana Wong
133 | CHAIR | Jan 1st wk | Assign coordinator for: Proclamations | Elaine & Mary
134 | POW/MIA HONORS CERE. | Jan 1st wk | Person to get items for and set up POW/MIA table
135 | PR | Jan lst wk | Send TWIM registration info to the manager of the Unaccompanied Housing Dormitories Manager to post on their bulletin boards
136 | PR | Jan lst wk | Follow up with APS on children's writing contest
137 | SEMINAR COORDINATORS | Jan 2nd wk | Contact seminar presenters—whether they want to stay for lunch; we will cover it.
138 | PROGRAM | Jan 2nd wk | Update on the morning event
139 | PROTOCOL | Jan 2nd wk | Wing CC -- invite him personally and ask him to make opening remarks | TOP 3
140 | PROGRAM | Jan 2nd wk | Name tags for the tea and breakfast
141 | PROTOCOL | Jan 2nd wk | Make Billeting reservations for keynote speaker | Teresa
142 | PROTOCOL | Jan 2nd wk | Mail VIP invitations (see list that Marsha sent to Teresa) | Teresa
143 | PROCLAMATION POC | Jan 2nd wk | Draft Proclamation for the Governor to sign; send to John Garcia’s office 2nd wk of Jan. | Mary & Elaine
144 | CO-CHAIR & EMCEE | Jan 2nd wk | MC script for program drafted | Elaine & MCs | Mary and I will review with Laurel Hull on Mon, Feb 14 | 2011-02-14
145 | CHAIR | Jan 2nd wk | Send keynote speaker bio to Kelly for program brochure | Elaine | Bio given to Kelly | 2011-01-09
146 | PROCLAMATION POC | Jan 2nd wk | Draft Proclamation for the ABQ Mayor to sign. Contact in the mayor's ofc: CABQ Veterans Liaison, ?? | Mary Cox
147 | TABLE CENTERPIECES | Jan 2nd wk | Confirm final decorations and table center pieces | Diana Wong
149 | FACILITY/ FOOD | Jan 2nd wk | Letter to SVS/CC to use donated food items for Continental Breakfast. | Marlene & Elaine | Meeting with MVC on Tues, Feb 15 @ 1330 | 2011-02-08
152 | VOLUNTEER COORDINATOR | Jan 2nd wk | Prepare spreadsheet of volunteers & tasks for day of event
153 | INVENTORY COORDINATOR | Jan 2nd wk | Arrange for 1 easel in MV Club to put large poster on | Marlene Mathis
154 | PR | Jan 3rd wk | Review planned publicity for February
155 | TREASURER | Jan 3rd wk | Final p/u of earlybird envelopes from POB, recording, delivery to Ethel. Award applications to Ethel. | Mary Cox
156 | TREASURER | Jan 3rd wk | Status of request for funds for special observance, if Top 3 is base sponsor | TOP 3
157 | REGISTRATION | Jan 3rd wk | Registration Subcommittee prepares name tags for the early bird registrations, along with lunch tickets. This first group will also include the TWIM Committee name tags with color TWIM logo and Service logos. Purchase tags for the bags for people to put their names on them. | Ethel Tilley
158 | T-SHIRTS | Jan 3rd wk | Place order for T-shirts | Kelly Aldrich | N/A | 2011-02-10
159 | CHAIR | Jan 3rd wk | If there will be a letter in the tote bags, need to write it now. | Elaine
160 | CHAIR | Jan 3rd wk | Send keynote speaker bio to MCs & incorporate into script | Elaine
161 | PROGRAM | Jan 4th wk | Status of healthscreens | Gloria C-S
162 | PROGRAM | Jan 4th wk | Confirm equipment requirements and arrangements for breakfast speaker | Marlene
164 | VICE CHAIR | Jan 4th wk | Set date to stuff tote bags. | Mary
165 | PROTOCOL | Jan 4th wk | Identify DVs who have confirmed | Teresa & Vitalia
166 | BREAKFAST SUBCOMM | Jan 4th wk | Prepare final of introduction of breakfast speaker, and her bio
167 | CHAIR | Jan 4th wk | Draft letter to go in Tote Bags | Chair
168 | CHAIR | Jan 4th wk | Assign 2-3 people to staff TWIM table in Exhibits Rm (will meet with Mary Cox on morning of event, she will give you the items, and then meet with her just before lunch for reconciliation) | Mary Cox
169 | VOLUNTEER COORDINATOR | Jan 4th wk | Get list of volunteers from V. Berry, and start plugging in names for assignments on Helper List | Elaine
170 | AWARDS | Jan 4th wk | After deadline for awards nominations (1/20/09), establish date for Award Panel to meet | Ethel Tilley
171 | REGISTRATION | Jan 4th wk | Update database with returned envelopes | Elaine & Ethel
172 | VOLUNTEER COORDINATOR | Feb 1st wk | Identify volunteers to assist with unloading of cars on morning of event | Victoria Berry
173 | TOP 3 | Feb lst wk | Identify Top 3 Ceremony Assistants (2) and get names to Kelly & Marsha for the program | TOP 3 & Kelly Aldrich
174 | ARRANGEMENTS | Feb 1st wk | Assign a Cake Coordinator (1)
175 | RIBBONS | Feb 1st wk | Determine # of ribbons for committee and helpers; buy them (ones for COMMITTEE, PRESENTER/SPEAKER, CHAIRMAN – 2, EXHIBITOR) | Mary Cox
176 | CHAIR/MCs | Feb lst wk | Next draft of Script | Emcees
177 | PROTOCOL | Feb 1st wk | Letter to 377 TRANS for DV vehicle, if one is needed. | TOP 3
178 | CENTERPIECES COORDINATOR | Feb 1st wk | Identify centerpieces for 2 head tables | Shirley McGuire
179 | PROTOCOL | Feb 1st wk | Make sure keynote speaker knows who the audience is, the Tribute theme, and that you tell the speaker not to get too technical or use a bunch of statistics. | Teresa
180 | AWARDS | Feb 1st wk | Awards committee chair gives names of winner to the chair to order the plaques | Ethel Tilley
181 | PLAQUES | Feb 2nd wk | Order tile or gift basket (if using this year) & plaques for Keynote Speaker and 2 Award Winners. Plaques must be paid for at the time of ordering. | Teresa
182 | PROTOCOL | Feb 2nd wk | Status of DVs who have RSVP'd. Protocol person to have spreadsheet with columns: Name, rank, organization, Opening, Luncheon, Both, Table - Opening, Table - Lunch, Paid ($), Escort? | Teresa
183 | CHAPLAIN POC | Feb 2nd wk | Contact Chaplain’s office to give them the background of TWIM, and the theme/focus for this year, and to keep the invocation to under 90 seconds. Confirm names/titles to Kelly& Marsha for the program
184 | Protocol | Feb 2nd wk | Review all A-V requirements including the needs of seminar speakers (N/A for 2010, but need to know for keynote speaker; & submit their info and meal choice | Marlene & Teresa
185 | EVALUATION | Feb 2nd wk | Bring final draft of evaluation form to mtg; get approval to go final | Diana Wong
186 | GRAPHICS | Feb 2nd wk | Work Order for Photographer -- *0815-1345 hrs for Opening Ceremony through end
187 | CHAIR | Feb 2nd wk | Meeting is at MV Club; review layout and logistics. Marlene to make ARRANGEMENTS for 2 tables to be set up for us. | Marlene
188 | TOTE BAGS | Feb 2nd wk | Review collections to date for tote bag items.
189 | CHAIR/MCs | Feb 2nd wk | Next draft of Script | Chair & MCs
190 | DOORPRIZES | Feb 2nd wk | Review listing of doorprizes
191 | MORNING REFRESHMENTS | Feb 2nd wk | Who is picking up donuts? | Mary
192 | REGISTRATION | Feb 2nd wk | Registration Subcommittee meets to prepare plastic bags for first group of regular registrations. | Ethel
193 | FACILITY | Feb 3rd wk | Notify Marlene Mathis whether you plan to attend the dinner for the keynote speaker on Thurs evening, Mar 4. Spouses are invited. The Committee picks up the tab for the dinner for the committee volunteers. | Marlene
194 | VOLUNTEER POC | Feb 3rd wk | Confirm helpers for day of event, including manning the doors, etc.
195 | SEMINAR COORDINATORS | Feb 3rd wk | Send or call reminder to seminar speakers on how to get into the base.
196 | REGISTRATION | Feb 3rd wk | Registration Subcomittee meets to stuff registration baggies with: name tag, ribbon, pin, doorprize ticket, meal ticket | Ethel
197 | CHAIR | Feb 3rd wk | Send email reminder to vocalists on how to get onto the base | Elaine
198 | DOORPRIZES | Feb 3rd wk | Establish final list of Door Prizes; email to Chair
199 | PLAQUE COORDINATOR | Feb 3rd wk | Check on status of plaque order (11 plaques) at Plaque Office in the Skills & Dev. Center | Chair or Vice Chair
200 | VOLUNTEER COORDINATOR | Feb 3rd wk | Next-to-last draft of DAY OF EVENT/HELPER list with Volunteer Coordinator & TOP 3 | Elaine & Victoria Berry
201 | CHAIR/MCs | Feb 3rd wk | Next draft of Script | Elaine
202 | FACILITIES | Feb 3rd wk | Final check of luncheon and FACILITY ARRANGEMENTS: Club, Exhibitors, Donut donation/purchase, communications set-up | Marlene
203 | PROTOCOL | Feb 3rd wk | Status on DVs | Teresa & Vitalia
204 | PROTOCOL | Feb 3rd wk | Place cards for DVs made | Teresa & Vitalia
205 | SEMINAR COORD | Feb 3rd Wk | Check with Ethel on how many are attending which seminar, and let each presenter know | Ethel
206 | SEMINAR COORD | Feb 3rd Wk | Ethel to notify Kelly Aldrich as to the number of people registered for each seminar, so she can determine which room they will go in and so note on program | Marlene/Kelly | Only one seminar, so N/A | 2011-02-10
207 | PROGRAM | Feb 3rd wk | Draft of program brochure | Elaine /Kelly |  | 2011-02-08
208 | TOTE BAG COORDINATOR | Feb 3rd wk | Stuff tote bags at meeting; start at 1530 hours | Mary Cox
209 | PROTOCOL | Feb 3rd wk | First draft - determine protocol seating – 2 head tables, + 1 table for WWII veterans | Teresa Wheeler
210 | AWARDS | Feb 3rd wk | Award-winner write-ups need to be condensed and sent to the Chair & MC for the script | Ethel Tilley
211 | CHAIR | Feb 3rd wk | Uniform for AD and civilians on day of main event | Chair
212 | PR | Feb 3rd wk | Inquire as to whether Nucleus reporter covering the event will want to stay for lunch. We will cover it. Get meal choice to Ethel.
213 | CHAIR | Feb 3rd wk | Identify senior military person to be greeter at door to identify DVs for a.m. and lunch | Top 3
214 | FACILITIES | Feb 3rd wk | Ensure club has order for 2 fruit & cheese trays and donut holes (25 dozen holes) | Marlene
215 | MORNING EVENT | Feb 3rd wk | Status of morning event
216 | FACILITY | Feb 3rd wk | Confirm with restaurant for keynote speaker dinner | Marlene
217 | REGISTRATION | Feb 4th wk | Need letter to SPTG/CC for allowing civilians on base during any exercise, e.g., FPCON BRAVO+, and plan of action to escort civilians from gate to Club | Ethel Tilley
218 | VOLUNTEER COORDINATOR & CHAIR | Feb 4th wk | Next-to-last draft helper list and “Day of Event” schedule | Elaine & Paula
219 | Vice Chair & REGISTRATION | Feb 4th wk | Mary & Ethel compare registration lists; make any last reconciliation changes.Give final count to Marsha. | Mary/Ethel
220 | REGISTRATION | Feb 4th wk | Registration Subcommittee meets to stuff remaining plastic bags with: name tags, TWIM pin, lunch ticket, and doorprize ticket; separate out the lunch-only names from the rest | Ethel
221 | PHOTOGRAPHER | Feb 4th wk | Email list of photos that need to be taken to POC for the photographer | Elaine
222 | PROTOCOL | Feb 4th wk | Purchase gift basket for keynote speaker at Southwest Gift Baskets, SE corner of Montgomery & Juan Tabo, next to the Great Bread company. | Teresa & Vitalia
223 | EXHIBITS | Feb 4th wk | Exhibits Coordinator coordinate w/Registration to ensure exhibitors are listed on the gate access list | Kelly Aldrich & Ethel Tilley
224 | CHAIR | Feb 4th wk | Appoint 2 people to be in uniform at Gibson gate to assist guards in getting people through quickly. | Paula
225 | CHAIR/MCs | Feb 4th wk | Email script to Chair & V-C and any committee members whose name is mentioned as doing something; also send it to Mary Cox. Get back comments and make final revisions.
226 | CHAIR | Feb 4th wk | Develop final list of tasks and confirm who is doing what. Assign a person to ring a bell or chimes to alert people to return to ballroom. | Elaine & Victoria
227 | EXHIBITS | T-4 | Make sure Marlene has layout of exhibit tables | Kelly
228 | CAKE COORDINATOR | T-4 | Give baker photo of what cake has to look like, and take the current colored TWIM Logo & Servicewomen stamp logo. Marsha to take logo graphic, stamp pin graphic, and picture of cake to Sam's Club on 3/2/09. Cakes needs to be p/u on Fri around 0700.
229 | CHAIR | T-4 | Pick up plaques from Base Plaque shop (Tel: 846-1070) | Elaine
230 | PROGRAM | T-4 | Drop off the following for printing: program and inserts, evaluation form, tote bag letter | Elaine, Kelly, Mary
231 | SIGNS | T-4 | Review SIGNS and remember to put them in car: 2 for registration (A-L, M-Z), 1 each for seminar room door, restroom signs and arrow signs for pointing to them. 3 'reserved table' signs: DV, WWII, TWIM in ballroom | Christina & Elaine
232 | Vice Chair & FACILITY/ FOOD | T-3 | Submit numbers for luncheon reservations – must have them to Club NLT 3/2/10. BACK OFF ON THE TOTAL REGISTERED BY 18 names on meat entrée and 2 names on veggie. | Marlene Mathis
233 | CHAIR | T-3 | Email final HELPER LIST and COUNTDOWN SCHEDULE | Elaine
234 | CHAIR | T-2 | Print out final notes for briefing to Committee on morning of event | Elaine
235 | CHAIR | T-2 | Finalize HELPER LIST/DAY OF EVENT SCHEDULE | Victoria & Elaine
236 | PROTOCOL | T-2 | Make sure the VOQ room for the keynote speaker and aide have the gifts in them | Teresa Wheeler
237 | CHAIR & EMCEES | T-2 | Review final SCRIPT. Print in 2 versions - 2 for MCs in large print (and put in notebooks for podiums), and 1 in regular size for Chair for Day of Event notebook. | Christina
238 | PROTOCOL | T-1 | Escorts pick-up vehicle for keynote speaker either on XXX 377 TRANS, @ XXXXXXX hrs. Make sure vehicle is clean | Teresa & Vitalia
239 | PROTOCOL | T-1 | Keynote speaker POC to pay room bill at Lodging | Teresa & Vitalia
240 | PROTOCOL | T-1 | Bring Gift Basket to club to give to Keynote Speaker | Elaine
241 | PR - ON BASE | T-1 | Retrieve large posters & bring to MV Club to chair
242 | SET-UP | T-1 | CLUB SET-UP WORKING SESSION | Marlene
243 | SET-UP | T-1 | Review day-of-event schedule/Helper List with everyone at set-up | Elaine & Victoria
244 | SET-UP | T-1 | AT SET-UP: Make a rough layout of the tables in the ballroom. | Victoria Berry
245 | SET-UP | T-1 | Remind club to open up on Fri NLT 0600. | Marlene Mathis
246 | SET-UP | T-1 | Run through morning event
247 | SET-UP | T-1 | MCs run through script | MCs & Ceremony Assistants
248 | SET-UP | T-1 | Protocol Briefing to Escorts | Elaine & Teresa
249 | EXHIBITS | T-1 | SET-UP: Bring copies of the exhibit room layout for committee members, so they can answer questions when exhibitors arrive. | Kelly
250 | REGISTRATION | T-1 | Provide SPs with list of guest speakers, attendees & program participants for Gate Guards at Gibson gate | Ethel Tilley
251 | EXHIBITS | T-1 | Assign one person to help w/Exhibit Room day of event | Kelly & Vitalia
252 | VOLUNTEER COORD & Chair | T-1 | SET-UP: Helper List/Day of Schedule list on hand at set-up | Elaine
253 | SET-UP VOLUNTEERS | T-1 | SET-UP: Fold Programs (if they are not already folder) and place one at each chair on the tables | Vice Chair
254 | REGISTRATION | T-1 | Registration: Deliver 2 registration lists of names to the Gibson gate for the gate guards and the 2 people who will be assisting them. | Ethel
255 | POW/MIA COORDINATOR | T-1 | On day of event: Person to pick up 1 red rose for POW/MIA table | Shirley McGuire
256 | FACILITY/ FOOD | T-1 | Dinner (1830 hrs) for Keynote Speaker w/Committee Members | Marlene Mathis
257 | ARRANGEMENTS | T-1 | P/U 1 red rose & bud vase for POW/MIA Table | Shirley McGuire
258 | SET-UP COLOR GUARD | T-1 | Color Guard rehearses - flags need to be in the following order: U.S., Army, Marine Corps, Navy, Air Force, Coast Guard, POW/MIA | Diana Wong
259 | PR | T-1 | To take notes and write news article for the Nucleus describing the day’s events | Laurel
260 | FACILITY | T-1 | Reconfirm with club on Thurs. -- 2 podiums and microphone are in place. | Marlene Mathis
261 | ALL | T-1 | Give a bear to each Committee member. | Mary
262 | ALL | T-1 | SEE HELPER LIST/DAY OF EVENT SCHEDULE FOR DETAILED TASKS TO BE DONE | All
263 | HELPERS | DAY OF EVENT | First thing in morning, put out the table centerpieces with the bears
264 | ALL | DAY OF EVENT | For entire day, SEE DAY OF EVENT SCHEDULE/HELPER LIST | ALL
265 | REGISTRATION | 2010-03-10 | Send final list to CHAIR & Vice Chair of names, addresses, and amounts of anyone who registered to attend, and who was going to pay at the door, but who did not show up. | Ethel Elaine
266 | EVERYONE | 2010-03-10 | Everyone to clean up and finish their documents, email to the chair. | EVERYONE
267 | ALL | 2010-03-10 | Everyone is to prepare an after-action report and email it to the committee NLT 3/12. | All
268 | EMCEES | 2010-03-10 | Add all changes to the script in the computer, and email final to CHAIR for file.
269 | EVALUATION | 2010-03-12 | Prepare summary of evaluation comments; email to committee | Diana
270 | ALL | 2010-03-12 | Gather all your receipts and bring to the 3/16 meeting for reimbursement. Call in or mail your info to Treasurer (Mary Cox) by 3/8 so she will have an idea of what the final financials will be. | All
271 | Vice Chair | 2010-03-15 | Prepare thank-you letters and mail out by March 24 (coordinate with the master list for sponsors and doorprize donors) | CHAIR, PR, DOORPRIZE COORD
272 | CHAIR | 2010-03-15 | Chair to write tax letters to donors of $250 or more | CHAIR
273 | PROGRAM | 2010-03-15 | Call Photographer and arrange to pick up the CD that has the photos on it. Preferably, we need 2 cy (1 for Kelly for posting on the website, and 1 for Marsha, for the scrapbook). Need some of the photos printed if possible. | Delia
274 | ALL | 2010-03-16 | Wrap-up meeting; review evaluations. Update ORG chart. Finalize countdown list. | Elaine
275 | ALL | 2010-03-16 | RECRUIT NEW COMMITTEE MEMBERS | All
276 | ALL | 2010-03-16 | Make your intentions known for serving on the Committee for 2011 | All
277 | CHAIR | 2010-03-20 | Chair to clean up the Countdown Schedule, Membership Roster, and Org Chart, for preparation for next Tribute. | CHAIR
278 | ALL | 2010-04-13 | 1st planning meeting for TWIM 2011, assuming it is scheduled | ALL

## Compatibility Report
Compatibility Report for CountdownSchedule2010X.xls
Run on 4/11/2009 17:42
The following features in this workbook are not supported by earlier versions of Excel. These features may be lost or degraded when you save this workbook in an earlier file format.
Significant loss of functionality | # of occurrences
Some cells have overlapping conditional formatting ranges. Earlier versions of Excel will not evaluate all of the conditional formatting rules on the overlapping cells. The overlapping cells will show different conditional formatting. | 1
'Sheet1'!B19:D19